## dataset
Project ID | Project Name | Department | Project Manager | Start Date | End Date | Budget (RM) | Actual Cost (RM) | Completion % | Status | Number of Issues | Number of Risks
PRJ-001 | ERP System Migration | Infrastructure | Priya Nair | 2024-02-09 | 2025-04-07 | 277000 | 267500 | 68 | On Track | 4 | 0
PRJ-002 | Mobile App Redesign | Security | Aisha Rahman | 2023-03-30 | 2024-02-05 | 1792000 | 1603000 | 72 | On Track | 0 | 4
PRJ-003 | Cloud Infrastructure Upgrade | IT Operations | Michael Lim | 2023-03-05 | 2024-03-24 | 2478000 | 3448600 | 12 | Delayed | 14 | 7
PRJ-004 | Cybersecurity Overhaul | Data & Analytics | Nurul Hana | 2023-05-28 | 2024-05-28 | 562000 | 700300 | 53 | Delayed | 8 | 6
PRJ-005 | Data Warehouse Implementation | Security | David Okonkwo | 2023-04-10 | 2024-04-14 | 337000 | 426900 | 41 | Delayed | 16 | 13
PRJ-006 | DevOps Pipeline Setup | DevOps | David Okonkwo | 2024-04-21 | 2025-05-15 | 1936000 | 2201100 | 21 | Delayed | 17 | 8
PRJ-007 | Customer Portal Development | IT Operations | Omar Khalid | 2023-11-04 | 2024-10-27 | 2107000 | 2416600 | 38 | At Risk | 12 | 6
PRJ-008 | AI Chatbot Integration | IT Operations | Rina Matsuda | 2024-03-04 | 2024-08-25 | 1481000 | 1419100 | 47 | On Track | 5 | 0
PRJ-009 | API Gateway Modernization | Infrastructure | David Okonkwo | 2023-12-25 | 2025-01-22 | 2114000 | 2557200 | 15 | Delayed | 10 | 12
PRJ-010 | Legacy Code Refactoring | IT Operations | Aisha Rahman | 2023-11-14 | 2025-01-08 | 2447000 | 2867700 | 38 | At Risk | 9 | 15
PRJ-011 | Microservices Architecture | Infrastructure | Aisha Rahman | 2024-04-17 | 2025-01-13 | 768000 | 939100 | 23 | Delayed | 18 | 9
PRJ-012 | BI Dashboard Rollout | Product | Michael Lim | 2024-02-12 | 2024-11-28 | 2113000 | 2011300 | 80 | On Track | 2 | 1
PRJ-013 | Identity Access Management | DevOps | Rina Matsuda | 2023-10-13 | 2025-01-06 | 1781000 | 2020300 | 44 | At Risk | 6 | 7
PRJ-014 | Network Segmentation Project | IT Operations | Priya Nair | 2023-06-04 | 2023-12-29 | 1035000 | 1048400 | 56 | On Track | 2 | 2
PRJ-015 | SaaS Platform Launch | Engineering | Priya Nair | 2024-03-05 | 2025-03-03 | 1592000 | 1849100 | 18 | Delayed | 17 | 13
PRJ-016 | Kubernetes Migration | Engineering | Kevin Park | 2024-02-06 | 2024-11-25 | 1714000 | 2088600 | 35 | Delayed | 6 | 8
PRJ-017 | Disaster Recovery Setup | IT Operations | Michael Lim | 2024-03-27 | 2024-09-16 | 530000 | 566300 | 10 | Delayed | 15 | 7
PRJ-018 | CRM System Upgrade | IT Operations | David Okonkwo | 2023-01-27 | 2023-06-02 | 931000 | 1026000 | 26 | Delayed | 11 | 14
PRJ-019 | Automated Testing Framework | Infrastructure | Kevin Park | 2023-05-06 | 2023-10-02 | 2079000 | 2236600 | 50 | At Risk | 7 | 6
PRJ-020 | Digital Transformation Phase 1 | Product | James Tan | 2023-12-17 | 2025-03-30 | 1164000 | 1504100 | 43 | Delayed | 6 | 8
PRJ-021 | IoT Platform Development | Infrastructure | Priya Nair | 2023-01-28 | 2024-05-20 | 2243000 | 2204600 | 50 | On Track | 5 | 2
PRJ-022 | Blockchain Proof of Concept | Infrastructure | Priya Nair | 2023-12-31 | 2025-04-29 | 992000 | 1312100 | 31 | Delayed | 16 | 8
PRJ-023 | E-Commerce Replatform | Security | Michael Lim | 2024-02-15 | 2025-05-28 | 1008000 | 966500 | 91 | On Track | 0 | 0
PRJ-024 | Data Privacy Compliance (PDPA) | Data & Analytics | Kevin Park | 2023-09-23 | 2024-03-30 | 1490000 | 2053200 | 32 | Delayed | 11 | 6
PRJ-025 | Real-Time Analytics Engine | Security | James Tan | 2023-08-21 | 2024-07-16 | 885000 | 1078800 | 49 | Delayed | 19 | 5
PRJ-026 | VPN Infrastructure Renewal | Digital Transformation | David Okonkwo | 2023-03-28 | 2024-08-26 | 571000 | 663100 | 68 | At Risk | 6 | 12
PRJ-027 | HR Payroll System Update | Product | Nurul Hana | 2023-12-07 | 2024-04-19 | 1701000 | 2228600 | 15 | Delayed | 17 | 7
PRJ-028 | Multi-Cloud Strategy | Product | Priya Nair | 2023-01-29 | 2023-07-15 | 2499000 | 2918200 | 29 | At Risk | 12 | 14
PRJ-029 | Zero Trust Architecture | Digital Transformation | David Okonkwo | 2023-06-09 | 2024-06-13 | 2325000 | 2051300 | 91 | On Track | 5 | 0
PRJ-030 | Product Analytics Tooling | Product | Nurul Hana | 2023-07-19 | 2024-12-12 | 944000 | 862900 | 77 | On Track | 1 | 4
PRJ-031 | Incident Management System | Infrastructure | Sarah Chen | 2024-03-05 | 2025-08-04 | 616000 | 615000 | 74 | On Track | 5 | 4
PRJ-032 | Employee Self-Service Portal | DevOps | Rina Matsuda | 2023-05-14 | 2024-05-10 | 701000 | 740600 | 38 | Delayed | 18 | 7
PRJ-033 | AI Model Governance Platform | Engineering | Priya Nair | 2023-06-26 | 2023-12-05 | 2019000 | 2205000 | 13 | Delayed | 11 | 13
PRJ-034 | Vendor Integration Hub | Digital Transformation | James Tan | 2023-02-28 | 2023-10-03 | 863000 | 866100 | 77 | On Track | 3 | 4
PRJ-035 | Low-Code Platform Adoption | Engineering | James Tan | 2024-03-29 | 2024-12-10 | 2150000 | 2407600 | 27 | Delayed | 13 | 13
PRJ-036 | Infrastructure as Code Migration | Digital Transformation | Rina Matsuda | 2023-09-11 | 2024-12-01 | 2223000 | 2677400 | 36 | At Risk | 11 | 8
PRJ-037 | SIEM Implementation | Digital Transformation | Priya Nair | 2024-03-02 | 2024-08-01 | 1687000 | 1814200 | 25 | Delayed | 12 | 6
PRJ-038 | Digital Onboarding Flow | Security | Sarah Chen | 2023-05-06 | 2024-09-04 | 712000 | 800100 | 43 | At Risk | 5 | 9
PRJ-039 | MLOps Pipeline Build | Product | Kevin Park | 2023-08-13 | 2024-11-27 | 465000 | 567600 | 52 | Delayed | 19 | 8
PRJ-040 | Contract Management System | Product | Nurul Hana | 2024-02-18 | 2024-11-07 | 1805000 | 1680400 | 91 | On Track | 2 | 0
PRJ-041 | Edge Computing Rollout | Infrastructure | Rina Matsuda | 2024-04-14 | 2025-02-23 | 154000 | 189600 | 28 | Delayed | 14 | 6
PRJ-042 | Helpdesk Automation | IT Operations | Michael Lim | 2023-04-18 | 2023-08-29 | 1167000 | 1196100 | 56 | On Track | 2 | 1
PRJ-043 | Unified Communications Platform | DevOps | Sarah Chen | 2024-02-20 | 2024-08-04 | 2277000 | 2513900 | 64 | At Risk | 8 | 6
PRJ-044 | Observability Stack Setup | Data & Analytics | Aisha Rahman | 2023-07-07 | 2024-05-09 | 376000 | 331900 | 50 | On Track | 2 | 0
PRJ-045 | Internal Knowledge Base | Security | James Tan | 2023-09-28 | 2025-03-12 | 578000 | 675500 | 45 | Delayed | 12 | 9
PRJ-046 | Supply Chain Visibility Tool | Product | Aisha Rahman | 2023-09-02 | 2024-01-26 | 741000 | 673600 | 64 | On Track | 5 | 2
PRJ-047 | Fintech API Layer | Security | Sarah Chen | 2024-04-01 | 2025-03-13 | 808000 | 814900 | 61 | On Track | 0 | 0
PRJ-048 | Security Awareness Training Platform | Engineering | Rina Matsuda | 2023-07-14 | 2024-07-01 | 2024000 | 1925900 | 87 | On Track | 5 | 3
PRJ-049 | Agile Transformation Initiative | Digital Transformation | Rina Matsuda | 2024-02-07 | 2025-01-21 | 1340000 | 1867800 | 31 | Delayed | 9 | 7
PRJ-050 | Tech Debt Reduction Sprint | DevOps | David Okonkwo | 2023-02-25 | 2024-07-27 | 611000 | 598800 | 61 | On Track | 3 | 1

## Summary
Project Portfolio Performance Dashboard
Tracks project health, budget, and risks across multiple projects.
📁 Total Projects |  |  | ✅ On Track |  |  | ⏰ Delayed
50 |  |  | 18 |  |  | 23
⚠️ At Risk |  |  | 💰 Total Budget (RM) |  |  | 📉 Total Actual (RM)
9 |  |  | 67213000 |  |  | 74699100
📊 Avg Completion |  |  | 🔴 Total Issues |  |  | 🎯 Total Risks
46.92 |  |  | 436 |  |  | 311
Breakdown by Department
Department | Total Projects | On Track | Delayed | At Risk | Avg Completion % | Total Issues | Total Risks
Engineering | 5 | 1 | 4 | 0 | 36 | 52 | 50
IT Operations | 8 | 3 | 3 | 2 | 35.375 | 70 | 52
Product | 8 | 4 | 3 | 1 | 56.375 | 64 | 44
Security | 7 | 3 | 3 | 1 | 57.4286 | 52 | 40
Data & Analytics | 3 | 1 | 2 | 0 | 45 | 21 | 12
Infrastructure | 8 | 3 | 4 | 1 | 42.375 | 79 | 47
DevOps | 5 | 1 | 2 | 2 | 45.6 | 52 | 29
Digital Transformation | 6 | 2 | 2 | 2 | 54.6667 | 46 | 37
ℹ️ Load the 'dataset' sheet into Power BI. Use DAX measures from README.md to replicate KPI cards above.